## Sheet1
Link | Test name | worker | browser | Cause of the problem | Our fix
https://starfishstorage.atlassian.net/browse/GUI-11130 | TC-SUB03 | sf-worker1 | firefox | FF verification issue - does not seem like a product issue | Still not fixed
https://starfishstorage.atlassian.net/browse/GUI-11132 | TC-CTD17 | sf-worker3 | chromium | Test expected .ag-overlay-no-rows-center but instead recives "Directory Not Found for Selected Dates" on compare message gird. On trace it looks like there is a dedicated error screen instead of “empty no rows” | Still not fixed
https://starfishstorage.atlassian.net/browse/GUI-11133 | TC-BTAGR16 | sf-chomp | chromium | Seems like e2e does not handle async query, and expects results right away. Test expects to see expect(responseJson).toHaveLength(1) as number but i receives "object": Matcher error: received value must have a length property whose value must be a number | Still not fixed
https://starfishstorage.atlassian.net/browse/GUI-11134 | TC-SRAH01 | sf-worker5 | chromium | Tow monitor console errors: "Unexpected error logged to the console" | Still not fixed
https://starfishstorage.atlassian.net/browse/GUI-11101 | TC-ANL33 | sf-worker2 | chromium | Screen verification error: "2137 pixels (ratio 0.01 of all image pixels) are different.". | Screen verified as in the % column, instead of the value there is still ‘-’, adding waiting for these values for a specific file on the grid + waiting for these files and on the canvas
https://starfishstorage.atlassian.net/browse/GUI-11021 | TC-TLBA03 | jenkins link not found | jenkins link not found | Overall test timeout | We have noticed that we are opening page, than change the scope of the page to recovery, then we open the volume. To reduce time we open direclty recovery on given volume
https://starfishstorage.atlassian.net/browse/GUI-10998 | TC-CTXA03 | jenkins link not found | jenkins link not found | Both tests have reached their time limit. | The time limits for both tests have been extended.
https://starfishstorage.atlassian.net/browse/GUI-11001 | TC-SRCS33, TC-SRCS34 | sf-worker10 | chromium | Search.addCondition was't awaited | Await was added to function call
https://starfishstorage.atlassian.net/browse/GUI-11004 | TC-NSUB13 | jenkins link not found | jenkins link not found | The chart was still loading when pw took the screenshot | It looks like we can wait for /query there, so I added that.
https://starfishstorage.atlassian.net/browse/GUI-11011 | TC-REC19 | jenkins link not found | jenkins link not found | Date picker script logic error | Added additional verification to make sure that history screen was trrigerd correctly
https://starfishstorage.atlassian.net/browse/GUI-11015 | TC-NBCTC05 | sf-chomp | chromium | Details panel data loading was taking too long, pw already started to work with not fully loaded details panel | WaitForDetailsPanelResponse was added
https://starfishstorage.atlassian.net/browse/GUI-11019 | TC-NDDET02 | jenkins link not found | jenkins link not found | Details panel data loading was taking too long, pw already started to work with not fully loaded details panel | WaitForDetailsPanelResponse was added
https://starfishstorage.atlassian.net/browse/GUI-11020 | TC-STG03 | jenkins link not found | jenkins link not found | Test timeout, 60s was to low for this test | Locally test runs 15-17 seconds but in failing run it took more then 60 seconds, increased timeout, changed login to more robust solution
https://starfishstorage.atlassian.net/browse/GUI-11035 | TC-RPS05, TC-PAM10, NPAM11 | jenkins link not found | firefox | TC-RPS05 timeout and tow monitor console errors: "Unexpected error logged to the console" | TC-PAM10, NPAM11 we added expectedErrors. TC-RPS05 Incressed timeout
https://starfishstorage.atlassian.net/browse/GUI-11036 | TC-TGST08 | jenkins link not found | firefox | Monitor console errors: "Unexpected error logged to the console". Test had missing expected SAML errors for firefox | We added expectedErrors
https://starfishstorage.atlassian.net/browse/GUI-11042 | TC-BCTC04 | jenkins link not found | jenkins link not found | Tests didn't wait for opening of detials panel it started verification still without showing other tabs on detials panel, which caused race in the application | WaitForDetailsPanelRespons was added
https://starfishstorage.atlassian.net/browse/GUI-11040 | TC-NSUB14 | jenkins link not found | jenkins link not found | The chart was still loading when pw tried to hover its path | Added waiting for query
https://starfishstorage.atlassian.net/browse/GUI-11043 | TC-CTD07 | jenkins link not found | jenkins link not found | Grid was not ready to work with playwright, it was still loading when pw tried to perform | Added waiting for query
https://starfishstorage.atlassian.net/browse/GUI-11044 | TC-HST04 | jenkins link not found | jenkins link not found | The problem associated with the time change | we had regexp for day before, day, but missing day after it strongly depens when data was created
https://starfishstorage.atlassian.net/browse/GUI-11012 | TC-BCTX | jenkins link not found | jenkins link not found | The problem associated with the time change | Those tests was failing because we were getting archie end time, in before all where it was changed to the timezone, the timezone logic should be run near action because before action timezone changed in Warsaw, and we used old time instead.
https://starfishstorage.atlassian.net/browse/GUI-11013 | TC-REZM12, TC-REZM13.2 | jenkins link not found | jenkins link not found | The problem associated with the time change | Setting the target time zone using .tz(PRIMARY_TIMEZONE) before formatting. This ensures that the date output is consistent and predictable, making the code robust and fixing test failures related to time zone discrepancies.
https://starfishstorage.atlassian.net/browse/GUI-11053 | TC-CTXA10 | jenkins link not found | jenkins link not found | test first run - timeout retry - timeout | setTestTimeout(120_000) was added
https://starfishstorage.atlassian.net/browse/GUI-11057 | TC-BRW14 | jenkins link not found | jenkins link not found | Monitor console errors: "Unexpected error logged to the console". | expectedWindowsOnError was added
https://starfishstorage.atlassian.net/browse/GUI-11006 | TC-CTXE | jenkins link not found | jenkins link not found | The problem associated with the time change | Changed range of compare two dates to avoid limit values which can cause the problems while time is changed.
https://starfishstorage.atlassian.net/browse/GUI-11034 | TC-CTD17,22,23 | jenkins link not found | jenkins link not found | The problem associated with the time change | Changed range of compare two dates to avoid limit values which can cause the problems while time is changed.
https://starfishstorage.atlassian.net/browse/GUI-11052 | TC-RPS05 | jenkins link not found | firefox | Firefox has problems pressing the PageDown key on the entire page and then focusing on the correct locator | Changed to specific locator instead of lcicking on a page.
https://starfishstorage.atlassian.net/browse/GUI-11058 | TC-CTD07 | jenkins link not found | jenkins link not found | Grid was not ready to work with playwright, it was still loading when pw tried to perform | Add more script logic to let playwright perform better
https://starfishstorage.atlassian.net/browse/GUI-11063 | TC-BRW13 | sf-tempworker2 | chromium | The problem associated with the time change | Modified method getTodayDateWithFormat to be not flaky for time changes
https://starfishstorage.atlassian.net/browse/GUI-11067 | TC-CTD22 | sf-worker6 | chromium | The problem associated with the time change | Changed range of compare two dates to avoid limit values which can cause the problems while time is changed
https://starfishstorage.atlassian.net/browse/GUI-11070 | TC-CTXZ11 | sf-worker2 | chromium | We were missing waiting for context menu | Add waiting to context menu to be hidden, after verification
https://starfishstorage.atlassian.net/browse/GUI-11079 | TC-JBAR03 | sf-worker1 | chromium | Missing asynchonous wiating for detail panel value | Changed .innerText() to web first assertion toHaveText, innerText took old value re-rendering toHaveText will await until value will change
https://starfishstorage.atlassian.net/browse/GUI-11081 | TC-TLBZ08 | sf-worker6 | chromium | Very long page loading time after selecting the volume zone; during this time, PW was already verifying the page elements, while other charts were still in the spinner phase, as a result of which PW clicked on a grid that was not ready. | Waiting for data query was added right after opening page.
https://starfishstorage.atlassian.net/browse/GUI-11089 | TC-SRCH10 | sf-worker1 | chromium | Accessing criteria through tabbing (in Old Browser) | Test removed due to a lack of stability. A similar case is tested in TC-NSRCH10.
https://starfishstorage.atlassian.net/browse/GUI-11102 | TC-TLBA12 | sf-chomp | chromium | Test timeout, 60s was to low for this test | We incressed test timeout
https://starfishstorage.atlassian.net/browse/GUI-11010 | with won't fix | dupliceted report | dupliceted report | dupliceted report | dupliceted report
https://starfishstorage.atlassian.net/browse/GUI-11014 | with won't fix | dupliceted report | dupliceted report | dupliceted report | dupliceted report
https://starfishstorage.atlassian.net/browse/GUI-11033 | with duplicate | dupliceted report | dupliceted report | dupliceted report | dupliceted report
https://starfishstorage.atlassian.net/browse/GUI-11041 | with won't fix | dupliceted report | dupliceted report | dupliceted report | dupliceted report
https://starfishstorage.atlassian.net/browse/GUI-11061 | with duplicate | dupliceted report | dupliceted report | dupliceted report | dupliceted report
https://starfishstorage.atlassian.net/browse/GUI-11064 | TC-BTAGR 16 with won't fix | sf-tempworker2 | chromium | 11 sec until user is logged in, backend must have been heavily used | No need to fix
https://starfishstorage.atlassian.net/browse/GUI-11016 | TC-JBAR04 TC-JBAP04 TC-JBRC04, TC-LOKI01,02, TC-SCAP08,09,19 | sf-worker1 | chromium | The problem associated with the time change | Anomaly related to time change, verified by the dev team, and there is no communication with the backend in the specified element, only: lastUpdated.value = new Date(); Anomaly related to time change.
https://starfishstorage.atlassian.net/browse/GUI-10869 | TC-BTAGR04 | sf-worker1 | chromium | Console request issue | Dev fix: https://github.com/StarfishStorage/sf-gui/pull/7280
https://starfishstorage.atlassian.net/browse/GUI-11009 | TC-BTAGR08 | sf-chomp | chromium | Deep problem explanation: https://starfishstorage.atlassian.net/browse/GUI-11009 | The issue has been resolved in GUI-10869.
https://starfishstorage.atlassian.net/browse/GUI-11062 | TC-BTAGR17 | sf-tempworker2 | chromium | Missing waiting for query | Added waitForQueryResponse function which will handle query_id for queryResult request
https://starfishstorage.atlassian.net/browse/GUI-11100 | TC-CTD17 | sf-worker10 | chromium | The problem associated with the time change | Changed time ranges for tests added missing steps from test update
https://starfishstorage.atlassian.net/browse/GUI-11118 | TC-CLI08 with won't fix | sf-chomp | chromium | The main reason is that the application takes 17 seconds to start up | The trace shows that the script only logs in after this time; before that, the application was loading. The first run timed out just before aborting the request to add TC_CLI:tag2, so the second attempt (retry 1) failed when trying to add this tag TC_CLI:tag2, because the previous run had already added it and did not abort.